## Cover
Budget management plan
Track the budget against spending, with the remaining amount and the share used worked out for you.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Budget
Budget management plan
Track the budget against spending, with the remaining amount and the share used worked out for you.
Amounts are examples in pounds. Type your own Approved, Committed, Actual, and Forecast. The rest updates on its own.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Currency | Pounds
Cost category | Work package | Approved | Committed | Actual to date | Forecast at completion | Variance | Percent spent | Status
Development | Core build | 54000 | 50000 | 36000 | 53000 | 1000 | 66.67% | On track
Testing and quality | Test and fix | 18000 | 16000 | 7000 | 17000 | 1000 | 38.89% | On track
Project management | Delivery | 18000 | 18000 | 11000 | 18000 | 0 | 61.11% | On track
Design | Screens and content | 12000 | 12000 | 10000 | 12500 | -500 | 83.33% | At risk
Setup and running | Hosting and tools | 12000 | 6000 | 6000 | 11000 | 1000 | 50% | On track
Contingency | Reserve | 6000 | 0 | 2000 | 4000 | 2000 | 33.33% | On track
Total |  | 102000 | 72000 | 115500 | 0On trackOn trackOn trackAt riskOn trackOn track
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Budget management plan. How to use this template.
A budget tracker that compares the approved budget with what is committed, what is actually spent, and the forecast at completion, and works out the variance for you.
Steps
1 | List each cost category and work package.
2 | Enter the Approved budget, the Committed amount, the Actual to date, and the Forecast at completion.
3 | The Variance and Percent spent are worked out for you, and the Total row adds everything up.
4 | Update it at least once a month and watch the Forecast, not just the Actual.
Columns
Column | What to put in it
Approved | The budget that was signed off.
Committed | Money promised in signed contracts, even before it is spent. An early warning of overruns.
Actual to date | What has actually been spent so far.
Forecast at completion | What you now expect the total to be. This is the number that matters most.
Variance | Approved minus Forecast. A negative number means you expect to overspend.
Tips
• | Watch the Forecast at completion. Actual to date tells you where you are, not where you will finish.
• | Track Committed early. It shows overruns before the money leaves.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Make Time Count, a publicly funded project.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.