## Cover
Burndown and velocity
Track work remaining across a sprint and how much the team delivers each sprint, ready to chart.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Burndown and velocity
Track work remaining across a sprint and how much the team delivers each sprint, ready to chart.
Project | Insta Fincorp (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
Sprint | Start | End | Committed points | Completed points | Carried over | Notes
Sprint 1 | Add date | Add date | 20 | 18 | 2 | A late change reduced the total
Sprint 2 | Add date | Add date | 22 | 22 | 0 | On plan
Sprint 3 | Add date | Add date | 21 | 19 | 2
Sprint 4 | Add date | Add date | 22 | 23 | 0 | Cleared the carry over
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Burndown and velocity. How to use this template.
A record of how much the team delivers each sprint, called velocity, and the base for a burndown chart of work remaining. It helps the team plan how much to take on.
Steps
1 | For each sprint, record the points committed and the points completed.
2 | The completed points are the team’s velocity for that sprint.
3 | Use the average velocity to plan how much to commit to next.
4 | For a burndown, add a small table of work remaining by day, and chart it.
Columns
Column | What to put in it
Committed points | The size of work the team took into the sprint.
Completed points | The size of work finished. This is the velocity.
Carried over | Work not finished, carried into the next sprint.
Tips
• | Use a few sprints of velocity to plan, not just one.
• | A steady velocity is a sign of a healthy team.
Definitions
Velocity | How many points a team completes in a sprint.
Burndown | A chart of work remaining over time, falling towards zero.
Example based on | Insta Fincorp, tracked across four sprints.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.