## Cover
Change request log
Capture and control changes to scope, with their impact on time and cost, and the decision on each.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Change request log
Capture and control changes to scope, with their impact on time and cost, and the decision on each.
Project | Retail Management Suite (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
ID | Date raised | Raised by | Change name | Description | Reason | Type | Impact on scope | Impact on time | Impact on cost | Impact on quality | Priority | Decision | Decided by | Requested date | Status
CR1 | Add date | Client | Second payment provider | Add a second payment provider | A key market needs it | Standard | New integration and extra testing | Two weeks | Increase | More testing needed | High | Approved | Client sponsor | Add date | In progress
CR2 | Add date | Store team | Loyalty on receipts | Add loyalty points to receipts | Requested by the stores | Standard | Small change to the till screen | Three days | Low | Little | Medium | Approved | Project Manager | Add date | Closed
CR3 | Add date | Client | Fourth country | Support a fourth country | A new expansion plan | Planned | Large, affects many areas | Six weeks | Increase | More testing across regions | High | Pending | Steering group | Add date | Open
CR4 | Add date | Support | Urgent tax fix | Correct a tax rate before month end | A rate changed | Emergency | One report affected | One day | Little | Must be right | High | Approved | Project Manager | Add date | Closed
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Change request log. How to use this template.
A record of every requested change to scope, with its impact on time and cost, and the decision on it, so the project never drifts without anyone agreeing to it.
Steps
1 | Log each change request with who raised it and why.
2 | Assess the impact on scope, time, and cost before any decision.
3 | Record the decision and who made it.
4 | Track the status until the change is done or closed.
Columns
Column | What to put in it
Impact on time | How much the change adds to the timeline.
Impact on cost | How the change affects the budget.
Decision | Approved, Rejected, or Pending.
Decided by | Who has the authority to decide.
Tips
• | No change without a decision. This is what stops quiet scope creep.
• | Always assess time and cost before saying yes.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Retail Management Suite, delivered across three countries.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Change request log. Summary.
These counts update as you fill in the Template tab.
By decision
Item | Count
Approved
Rejected
Pending
By status
Item | Count
Open
In progress
Closed
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.