## Cover
Communication plan
Agree who to keep informed, why, how often, and in what form.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Communication plan
Agree who to keep informed, why, how often, and in what form.
Project | GameSol (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
Audience | Purpose | Key message | Level of detail | Channel or format | Frequency | Owner | Direction | Feedback or response
Client sponsors | Share progress and agree decisions | What is on track, what needs a decision | Low | Written update and a call | Weekly | Project Manager | Two way | Decisions agreed on the call
Delivery team | Plan the work and clear any blockers | What we finish today, what is in the way | High | Short meeting | Daily | Project Manager | Two way | Blockers raised and picked up
Teams across time zones | Make sure no one is left behind | Decisions and notes from each day | Medium | Written notes shared with everyone | Daily | Project Manager | One way | Questions answered next day
Wider stakeholders | Give an overall view of progress | Where the project stands overall | Low | Status report | Every two weeks | Project Manager | One way | Comments by reply
End users | Prepare people for the change | What is changing and when | Medium | Email and short guide | At key points | Business analyst | One way | Support inbox for questions
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Communication plan. How to use this template.
A plan of who needs to hear what, why, how often, and in what form, so nobody is left out and messages are not missed.
Steps
1 | List each audience, from sponsors to the wider team.
2 | For each one, write the purpose and the key message.
3 | Choose a channel and a frequency that suit that audience.
4 | Give every line an owner, so the message is always sent.
Columns
Column | What to put in it
Audience | The group who needs the information.
Key message | The main thing they need to take away.
Channel or format | How it is sent, for example a call, a report, or a note.
Direction | One way if you are informing, Two way if you need a response.
Tips
• | Different audiences need different detail. Sponsors want the headline, the team wants the detail.
• | Across time zones, write things down so no one depends on being in the room.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | GameSol, built by teams across several countries and time zones.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.