## Cover
Decision log
Record the main decisions, the options considered, and the reason for each choice.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Decision log
Record the main decisions, the options considered, and the reason for each choice.
Project | Moneyer (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
ID | Date | Category | Decision | Context | Options considered | Choice | Rationale | Decision maker | Impact | Status | Review date
D1 | Add date | Design | How to show spending | Users must understand their money at a glance | A simple list, or charts | Charts with a list below | Clear at a glance while keeping the detail | Client and Project Manager | Medium | Approved | Add date
D2 | Add date | Scope | How budgets are set | Balance simplicity against control | Automatic, or by hand | By hand first, automatic later | A simpler first version, agreed with the client | Client | Medium | Approved | Add date
D3 | Add date | Process | How each screen is agreed | Avoid repeated rework on the screens | Build then review, or agree first | Agree each screen first with the designer | Less repeated work and a consistent look | Project Manager | Low | Approved | Add date
D4 | Add date | Technical | Which payment provider to use | The provider affects cost and reach | Provider A, or provider B | Provider A for this release | Better fit for the main market, agreed with the client | Client and Project Manager | High | Approved | Add date
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Decision log. How to use this template.
A record of the main decisions, the options that were weighed, and the reason for each choice, so no one has to relitigate settled questions.
Steps
1 | Add a row when a decision of any weight is made.
2 | Write the context, the options considered, and the choice.
3 | Always fill in the Rationale. It is the most useful column later.
4 | Record who made the decision and set the Status.
Columns
Column | What to put in it
Context | Why the decision was needed.
Options considered | The choices that were on the table.
Rationale | The reason the choice was made. This prevents the question coming back.
Status | Proposed, Approved, Rejected, or Superseded.
Tips
• | Log the rejected options too. It stops people reopening them.
• | Record decisions while they are fresh, not at the end of the project.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Moneyer, a personal finance application.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Decision log. Summary.
These counts update as you fill in the Template tab.
By status
Item | Count
Proposed
Approved
Rejected
Superseded
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.