## Cover
Defect and bug log
Track every fault found, with its severity, its status, who found it, and who is fixing it.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Defect and bug log
Track every fault found, with its severity, its status, who found it, and who is fixing it.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
ID | Title | Description | Steps to reproduce | Severity | Priority | Status | Found in | Found by | Assigned to | Date raised | Date resolved | Notes
B1 | An unauthorised view is not logged | Access is refused but not written to the log | Sign in without rights, then try to open a record | High | High | Open | System test | Tester | Developer | Add date
B2 | Totals round wrongly | Statement totals are a penny out | Open a statement with many rows | Medium | Medium | Fixed | System test | Tester | Developer | Add date | Add date | Retested
B3 | A report is slow for large data | A report is slow over a long period | Open a report over a long period | Low | Low | In progress | System test | Tester | Developer | Add date
B4 | Locking fails on an old device | Locking behaves differently on some old devices | Use an older Android device | High | High | Closed | System test | Tester | Developer | Add date | Add date | Fixed and retested
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Defect and bug log. How to use this template.
A record of every fault found, with its severity, its status, who found it, and who is fixing it, so nothing is lost and the worst faults are fixed first.
Steps
1 | Raise a defect for each fault, with a clear title and steps to reproduce it.
2 | Set the severity and the priority, and assign an owner.
3 | Move the status from Open through to Closed as it is fixed and retested.
4 | Do not close a defect until it has been retested.
Columns
Column | What to put in it
Severity | How serious the fault is: Critical, High, Medium, or Low.
Priority | How soon it should be fixed.
Steps to reproduce | The exact steps to make the fault happen, so it can be fixed and checked.
Status | Open, In progress, Fixed, Retest, Closed, or Rejected.
Tips
• | Fix the critical and high severity faults first.
• | Good steps to reproduce save hours. Write them clearly.
Definitions
Severity | How much harm the fault causes.
Priority | How urgently it should be fixed. A small fault can still be urgent.
Example based on | Make Time Count and Insta Fincorp, faults found during testing.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Defect and bug log. Summary.
These counts update as you fill in the Template tab.
By severity
Item | Count
Critical
High
Medium
Low
By status
Item | Count
Open
In progress
Fixed
Retest
Closed
Rejected
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.