## Cover
Delivery board
See every task and the stage it has reached, from to do through to completed.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Delivery board
See every task and the stage it has reached, from to do through to completed.
Project | Insta Fincorp (example)
Prepared by | Nirmal Prajapati
Sprint | Add the sprint or week
ID | Task | Description | Type | Stage | Priority | Owner | Estimate days | Sprint | Blocked | Blocker reason | Notes
T1 | Sign in and user permissions | Secure sign in and access levels | Feature | Done | High | Development | 4 | Sprint 1 | No |  | Delivered
T2 | The main dashboard | Accounts overview screen | Feature | Done | High | Development | 5 | Sprint 1 | No |  | Delivered
T3 | The loan application | Apply, review, and approve a loan | Feature | In progress | High | Development | 8 | Sprint 2 | No |  | On track
T4 | Matching of payments | Match incoming payments to accounts | Feature | In progress | Medium | Development | 6 | Sprint 2 | Yes | Waiting on the payment service | Chase the supplier
T5 | The sign up screens | New customer sign up | Feature | Client review | Medium | Design | 3 | Sprint 2 | No |  | Waiting for approval
T6 | Fix statement totals | Totals were rounding wrongly | Bug | To do | High | Development | 2 | Sprint 3 | No |  | Reported in testing
T7 | Exporting statements | Download account statements | Feature | Backlog | Low | Development | 3 | Sprint 3 | No |  | Planned for the next round
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Delivery board. How to use this template.
A simple task board in a spreadsheet, so anyone can see every task, its stage, its owner, and whether it is blocked.
Steps
1 | Add one row per task, with a short ID and a clear title.
2 | Set the Stage and the Priority, and give it an owner.
3 | Mark Blocked as Yes the moment something is holding a task up.
4 | Filter by Stage or Owner to run a stand up. Watch the In progress count.
Columns
Column | What to put in it
Stage | Where the task is, from Backlog through to Done.
Priority | How important the task is.
Estimate days | A rough size in working days.
Blocked | Yes if something is stopping the task from moving.
Tips
• | Keep the number of In progress tasks small. Finishing beats starting.
• | Clear blocked items first in every stand up.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Insta Fincorp, a finance platform for accounts and payments.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Delivery board. Summary.
These counts update as you fill in the Template tab.
Work by stage
Item | Count
Backlog
To do
In progress
Client review
Done
Blocked
Item | Count
Blocked items
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.