## Cover
Delivery plan
Set out the phases of the work, what each phase covers, and where each one stands.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Delivery plan
Set out the phases of the work, what each phase covers, and where each one stands.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
Phase | Objective | Key deliverables | Owner | Start | End | Percent complete | Dependencies | Status | Notes
Discovery | Agree the goals and the way of working | Agreed goals, ways of working | Project Manager | Week 1 | Week 1 | 100% | None | Done | Kick off held
Research | Understand the current tools and agree the single system | Review of the current tools, agreed scope | Business analyst | Week 1 | Week 3 | 100% | Discovery complete | Done | Scope signed off
Build | Build the main system and move the shared information across | Working system, data moved | Delivery team | Week 4 | Week 10 | 100% | Scope agreed | Done | On plan
Preparation | Bring each organisation onto the single system | Training, written guidance | Project Manager | Week 11 | Week 14 | 60% | Build complete | In progress | Onboarding under way
Launch | Switch over and obtain approval | Go live, formal sign off | Project Manager | Week 15 | Week 15 | 0% | Testing complete | Planned
Support | Support closely after launch and review what to improve | Support notes, review | Delivery team | Week 16 | Week 20 | 0% | Launch complete | Planned
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Delivery plan. How to use this template.
A plain plan of the phases of the work, what each phase is meant to achieve, what it delivers, and where it stands.
Steps
1 | List the phases in order, from the first to the last.
2 | For each phase, write the objective and the key deliverables.
3 | Give each phase an owner, a start, and an end.
4 | Update Percent complete and Status as the work moves on.
Columns
Column | What to put in it
Phase | A stage of the work, for example Research or Build.
Objective | What this phase is meant to achieve.
Key deliverables | The main things this phase produces.
Percent complete | How far the phase has progressed, from 0 to 100 percent.
Status | Done, In progress, or Planned.
Tips
• | Keep phases few and clear. Five is usually enough.
• | Put the most valuable work early, so the important parts land first.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Make Time Count, a shared case system for several public bodies.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Delivery plan. Summary.
These counts update as you fill in the Template tab.
By status
Item | Count
Done
In progress
Planned
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.