## Cover
Delivery schedule
List the milestones, their target dates, and their status at a glance.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Delivery schedule
List the milestones, their target dates, and their status at a glance.
Project | EduSec (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
ID | Milestone | Description | Deliverable | Owner | Baseline week | Forecast week | Actual week | Variance weeks | Status | Dependencies | Notes
M1 | Requirements agreed | Scope and needs signed off with the client | Signed scope | Project Manager | 2 | 2 | 2 |  | Done | None | Agreed on time
M2 | Core records built | Student and staff records working | Working records | Delivery team | 8 | 9 | 9 |  | Done | Requirements agreed | One week late, recovered
M3 | Reporting and oversight | Manager reports and daily tasks | Reports | Delivery team | 12 | 12 |  |  | In progress | Core records built | On plan
M4 | Testing complete | Client testing signed off | Test sign off | QA lead | 14 | 14 |  |  | Planned | Reporting built
M5 | Launch | Go live and formal approval | Live system | Project Manager | 15 | 15 |  |  | Planned | Testing complete
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Delivery schedule. How to use this template.
A milestone tracker that compares the baseline plan with the current forecast, so slippage shows early.
Steps
1 | List the milestones in order and give each a short ID.
2 | Set the Baseline week when you first agree the plan, then do not change it.
3 | Update the Forecast week as things change. The Variance is worked out for you.
4 | Record the Actual week when a milestone is met, and update the Status.
Columns
Column | What to put in it
Baseline week | The week the milestone was first planned for. Keep it fixed.
Forecast week | The week you now expect it. Update this as the plan changes.
Actual week | The week it actually happened.
Variance weeks | Forecast minus Baseline. A positive number means it is running late.
Status | Done, In progress, or Planned.
Tips
• | Never change the baseline once it is agreed. That is what makes slippage visible.
• | A small positive variance early is a signal to act, not to wait.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | EduSec, an institute management system used in several countries.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Delivery schedule. Summary.
These counts update as you fill in the Template tab.
By status
Item | Count
Done
In progress
Planned
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.