## Cover
Development plan
Plan the development work on a product in one place. List each piece of work, what it delivers, how important it is, the stage it is at, and a month by month view of when it moves from design to build to test and then live.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Development plan
Development plan
Plan the development work on a product in one place. List each piece of work, what it delivers, how important it is, the stage it is at, and a month by month view of when it moves from design to build to test and then live.
Product | Customer booking and account system (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
Item | Work item | What it delivers | Type of work | Requested by | Reference | Priority | Stage now | Planned to go live | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
1 | Online booking calendar | Customers book a slot online and see what is free | New feature | Client | REF 101 | High | Build | Month 5 | Design | Build | Build | Test | Check | Live | Live | Live | Live | Live | Live | Live
2 | Faster reports page | The reports page shows its results quickly | Improvement | Users | REF 102 | Medium | Test | Month 4 |  | Design | Build | Test | Check | Live | Live | Live | Live | Live | Live | Live
3 | Fix sign in on older phones | People on older phones can sign in again | Fix | Support | REF 103 | High | Final check | Month 3 |  | Build | Test | Check | Live | Live | Live | Live | Live | Live | Live | Live
4 | Move to the supported database | The system stays safe and keeps its support | Technical work | Internal | REF 104 | High | Design | Month 8 |  |  |  | Design | Design | Build | Build | Test | Check | Live | Live
5 | Single sign on for staff | Staff sign in once and reach every tool | New feature | Client | REF 105 | Medium | Build | Month 7 |  |  | Design | Build | Build | Test | Check | Live | Live | Live | Live
6 | Two step sign in | A second check when signing in, to keep accounts safe | Security | Internal | REF 106 | High | Design | Month 8 | Month 5: Design; Month 6: Build; Month 7: Test; Month 8: Check; Month 9: Live; Month 10: Live; Month 11: Live
7 | Tidy up unused code | The system becomes easier to look after | Technical work | Internal | REF 107 | Low | Waiting to start | Month 11 | Month 8: Design; Month 9: Build; Month 10: Build; Month 11: Test
8 | Close accounts left unused for a year | Protects data by closing accounts nobody uses | Technical work | Internal | REF 108 | Medium | Waiting to start | Month 9 | Month 6: Design; Month 7: Build; Month 8: Test; Month 9: Check; Month 10: Live; Month 11: Live
9 | Reminders by text message | Customers get a text reminder about a booking | New feature | Users | REF 109 | Medium | On hold | Month 11 | Month 7: Hold; Month 8: Hold; Month 9: Design; Month 10: Build; Month 11: Build; Month 12: Test
10 | Pay by card in the app | Customers can pay inside the app | New feature | Client | REF 110 | High | Design | Month 9 | Month 6: Design; Month 7: Design; Month 8: Build; Month 9: Build; Month 10: Test; Month 11: Check
11 | Export reports to a spreadsheet | A manager can download a report as a spreadsheet | Improvement | Users | REF 111 | Low | Build | Month 6 |  |  |  | Design | Build | Test | Check | Live | Live | Live | Live
12 | More languages in the app | More people can use the app in their own language | New feature | Client | REF 112 | Low | Waiting to start | Month 12 | Month 9: Design; Month 10: Build; Month 11: Build; Month 12: Test
Stage key
Waiting to start | Agreed and in the queue. Not started yet.
Design | Working out exactly what to build and how it should look.
Build | Writing the software.
Test | Checking it works and putting right anything that is wrong.
Final check | A last check in a copy of the live system before customers see it.
Live | Released and being used by customers.
On hold | Paused for now, with the reason written down.
At a glance
Waiting to start
Design
Build
Test
Final check
Live
On hold
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Development plan. How to use this template.
A rolling plan of the development work on a product. It lists each piece of work, what it delivers, who asked for it, how important it is, the stage it is at now, and a month by month view of when it moves from design to build to test, then a final check, and then live.
Steps
1 | List each piece of work on its own row, with a short note on what it delivers.
2 | Set the type of work, who asked for it, and how important it is.
3 | Set the stage each item is at now, and the month you expect it to go live.
4 | Colour the month cells to show the item moving through design, build, test, the final check, and then live. Update the plan every week or two.
Columns
Column | What to put in it
Work item | The piece of work, named in a few plain words.
What it delivers | The benefit to the customer or the business, in one line.
Type of work | Whether it is a new feature, an improvement, a fix, technical work, or a security item.
Requested by | Who asked for it. The client, the users, the internal team, or support.
Reference | A short code so you can find the item in your tracking tool.
Priority | How important the item is. High, Medium, or Low.
Stage now | Where the item is today. Waiting to start, Design, Build, Test, Final check, Live, or On hold.
Planned to go live | The month you expect customers to start using it.
Month columns | The timeline. Colour each month to show the stage the item is in that month.
Tips
• | Keep one piece of work on each row. If the title has the word and in it, it may be two items.
• | Move an item to Live only once customers can really use it, not when the building is finished.
• | Review the plan on the same day each week or two, so people come to trust it.
Definitions
Stage | A step in the life of a piece of work, from design through to live.
Final check | A last check in a copy of the live system, so problems are found before customers do.
On hold | Paused for now. Always write down why, and what would restart it.
Example based on | Make Time Count, a shared case system for several public bodies.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.