## Cover
Earned value report
Compare planned, earned, and actual value, and work out the schedule and cost performance for you.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Earned value report
Compare planned, earned, and actual value, and work out the schedule and cost performance for you.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Report date | Add the date
Item | Planned value | Earned value | Actual cost | Schedule variance | Cost variance | Schedule index | Cost index
Development | 40000 | 38000 | 39000
Testing and quality | 12000 | 12000 | 11000
Project management | 12000 | 12000 | 12000
Design and setup | 16000 | 15000 | 16000
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Earned value report. How to use this template.
A way to compare what you planned to have done, what you have actually earned, and what it has cost, and to work out whether you are ahead or behind on both time and money.
Steps
1 | For each item, enter the planned value, the earned value, and the actual cost.
2 | The variances and the performance indexes are worked out for you.
3 | Read the indexes: one is on plan, below one is behind, above one is ahead.
4 | Act on any item that is behind on schedule or over on cost.
Columns
Column | What to put in it
Planned value | The value of the work that should be done by now.
Earned value | The value of the work actually done.
Actual cost | What has actually been spent.
Schedule index | Earned divided by planned. Below one means behind schedule.
Cost index | Earned divided by actual cost. Below one means over cost.
Tips
• | Watch the indexes over time, not just once. A falling index is an early warning.
• | Earned value is the value done, not the money spent.
Definitions
Earned value | The agreed value of the work that has actually been completed.
Variance | The difference between two figures. A negative one is usually bad.
Example based on | Make Time Count, its planned, earned, and actual figures.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.