Gap analysis

Compare how things work now with how they should work, and set out the gaps and the actions to close them.

## Document control

| Project | Add the project |
| --- | --- |
| Author | Nirmal Prajapati |
| Owner | Add the owner |
| Version | 1.0 |
| Date | Add the date |
| Status | Draft |

## Version history

| Version | Date | Author | Summary of change |
| --- | --- | --- | --- |
| 1.0 | Add the date | Nirmal Prajapati | First version |

# 1. Purpose

This gap analysis compares how things work today with how they should work, sets out the gaps between the two, and lists the actions to close them. It helps agree what the project must change. The example is based on Make Time Count.

# 2. Current state

Each organisation keeps its own notes, so a person is recorded in several places, updates are missed, and staff cannot see the full picture. Acting on a case is slow.

# 3. Future state

All authorised organisations work from one shared record, updated in one place, with suggestions on a case and reports for managers. People are helped sooner.

# 4. Gaps and actions

| Area | Now | Should be | Gap | Action | Owner |
| --- | --- | --- | --- | --- | --- |
| Records | Separate notes per body | One shared record | No shared record exists | Build the shared record | Delivery team |
| Access | Anyone with the file | Access by role and body | No access control | Build access control | Delivery team |
| Reporting | Little visibility | Usage and outcome reports | No reports | Build reporting | Delivery team |
| Accessibility | Not accessible | Meets the standard | Standard not met | Design to the standard | Designer |

# 5. Recommendations

Close the record and access gaps first, since everything else depends on them. Build reporting once the records are in place. Design to the accessibility standard throughout.

# 6. Priorities

- First: the shared record and access control.

- Then: reporting.

- Throughout: accessibility.