## Cover
Lessons learned review
Capture what went well and what to improve, with an action and an owner for each.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Lessons learned review
Capture what went well and what to improve, with an action and an owner for each.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Review date | Add the date
ID | Date identified | Category | What happened | Type | Impact | Root cause | Recommendation | Action | Owner | Status | Date closed
L1 | Add date | Planning | Weekly risk reviews caught problems early | Went well | Fewer surprises near launch | A standing weekly review was in place | Keep the weekly risk review on every project | Add it to the standard way of working | Project Manager | Closed | Add date
L2 | Add date | Requirements | The AI scope was vague at first | To improve | Some rework early on | The AI feature was not defined concretely | Define AI features concretely before the build | Add a definition step before the build | Business analyst | Actioned | Add date
L3 | Add date | Delivery | Accessibility was planned from day one | Went well | No late accessibility fixes | Accessibility was in the plan from the start | Plan accessibility from the start | Keep it in the standard checklist | Delivery team | Closed | Add date
L4 | Add date | Stakeholders | Some organisations joined late | To improve | Slower onboarding | Not all bodies were engaged in planning | Bring all the bodies in during planning | Invite every body to the kick off | Project Manager | Open
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Lessons learned review. How to use this template.
A review that captures what went well and what to improve, and turns each point into an action with an owner, so the next project starts wiser.
Steps
1 | Hold the review at the end of the project, or at key points along the way.
2 | For each point, note what happened and whether it went well or should improve.
3 | Write a clear recommendation and give it an owner.
4 | Track the status until each action is closed.
Columns
Column | What to put in it
Type | Went well, or To improve.
Impact | What effect it had on the project.
Recommendation | What to do differently, or keep doing, next time.
Status | Open, Actioned, or Closed.
Tips
• | Be specific and blameless. The point is to learn, not to blame.
• | A lesson with no action changes nothing. Give each one an owner.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Make Time Count, reviewed after delivery.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Lessons learned review. Summary.
These counts update as you fill in the Template tab.
By type
Item | Count
Went well
To improve
By status
Item | Count
Open
Actioned
Closed
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.