## Cover
Priority list and backlog
Sort the work by priority as user stories, so the most important is agreed and delivered first.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Priority list and backlog
Sort the work by priority as user stories, so the most important is agreed and delivered first.
Project | EduSec (example)
Prepared by | Nirmal Prajapati
Release | Add the release
ID | Epic | User story | Acceptance criteria | Priority | Value | Effort points | Owner | Release | Status | Dependencies
F1 | Records | As an administrator, I want to hold student and staff records, so that everyone works from the same details | A record can be created, viewed, and updated | Must have | High | 8 | Business analyst | Release 1 | Done | None
F2 | Daily work | As a teacher, I want to record attendance and daily tasks, so that the day runs in one place | Attendance can be taken and seen | Must have | High | 8 | Delivery team | Release 1 | In progress | Records
F3 | Access | As an administrator, I want the right access per user, so that people see only what they should | Each role sees the right screens | Must have | High | 5 | Delivery team | Release 1 | In progress | Records
F4 | Reporting | As a manager, I want reports, so that I can decide with a clear view | A manager can open usage reports | Should have | High | 5 | Delivery team | Release 2 | Planned | Daily work
F5 | Messaging | As a parent, I want simple updates, so that I stay informed | A parent receives an update | Could have | Medium | 3 | Product team | Release 2 | Planned | Access
F6 | Mobile | As a user, I want a separate mobile application, so that I can work on the go | Not planned for this release | Will not have this time | Medium | 13 | Product team | Later | Planned | None
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Priority list and backlog. How to use this template.
A priority list that sorts features into Must have, Should have, Could have, and Will not have this time, so the right work is agreed first.
Steps
1 | List each feature with a short description.
2 | Agree the Priority with the client. Be honest about what will not make this release.
3 | Add the Value and the Effort to help settle close calls.
4 | Track the Status as features are built.
Columns
Column | What to put in it
Priority | Must have, Should have, Could have, or Will not have this time.
Value | How much this feature is worth to the users or the business.
Effort | How much work it is likely to take.
Tips
• | Keep the Must have list short. If everything is a must, nothing is.
• | A feature with high value and low effort is usually a quick win.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | EduSec, where the core records came first and extras followed.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Priority list and backlog. Summary.
These counts update as you fill in the Template tab.
By priority
Item | Count
Must have
Should have
Could have
Will not have this time
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.