## Cover
Project dashboard
See the key numbers on one page: status, schedule, budget, risks, and progress.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Project dashboard
See the key numbers on one page: status, schedule, budget, risks, and progress.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Report date | Add the date
Area | Metric | Value | Target | Status | Trend | Notes
Overall | Overall health | On track | On track | On track | Flat
Schedule | Milestones on time | 3 of 4 | All | At risk | Flat | Reporting a little behind
Budget | Percent of budget used | 58% | In line | On track | Flat
Scope | Change requests open | 1 | Low | On track | Flat
Risk | High severity risks open | 2 | 0 to 3 | On track | Down
Quality | High severity defects open | 1 | 0 | At risk | Down | One open, being fixed
Progress | Work complete | 70% | 70% | On track | Up
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Project dashboard. How to use this template.
The key numbers of the project on one page, so anyone can see its health at a glance, across status, schedule, budget, scope, risk, quality, and progress.
Steps
1 | Choose the few numbers that best show the health of the project.
2 | For each, record the value, the target, the status, and the trend.
3 | Keep it to one page. A dashboard is for a glance, not a deep read.
4 | Update it on the same day each week, next to the status report.
Columns
Column | What to put in it
Value | The current figure.
Target | What good looks like.
Status | On track, At risk, or Off track.
Trend | Whether it is getting better, holding, or getting worse.
Tips
• | Fewer numbers, chosen well, beat many. Pick the ones that drive decisions.
• | Colour and trend together tell the story fast.
Definitions
Metric | A number that shows how the project is doing.
Trend | The direction the number is moving.
Example based on | Make Time Count, its weekly health at a glance.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.