## Cover
Project schedule
Plan the tasks, who owns each one, when it starts, and how long it takes.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Schedule
Project schedule
Plan the tasks, who owns each one, when it starts, and how long it takes.
Project | Leapwise Advisory (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
ID | Task | Owner | Start week | Weeks | Percent complete | Predecessor | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
1 | Discovery and goals | Project Manager | 1 | 1 | 100% |  | Done
2 | Requirements and planning | Project Manager | 2 | 1 | 100% | 1 | Done
3 | Design and approval | Client | 2 | 2 | 100% | 2 | Done
4 | Build and delivery | Delivery team | 3 | 3 | 50% | 3 | In progress
5 | Partner integration | Outside partner | 3 | 3 | 40% | 3 | In progress
6 | Testing | Delivery team | 6 | 2 | 0% | 4 | Planned
7 | Handover and go live | Project Manager | 8 | 1 | 0% | 6 | Planned
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Project schedule. How to use this template.
A project schedule with a task list and a simple bar chart, showing who owns each task, when it starts, how long it takes, and how the tasks depend on each other.
Steps
1 | List the tasks in order, each with an owner.
2 | Set the Start week and the number of Weeks. The bars on the right show the timeline.
3 | Add the Predecessor, the task that must finish before this one starts.
4 | Update Percent complete and Status as the work moves on.
Columns
Column | What to put in it
Start week | The week the task begins.
Weeks | How many weeks the task takes.
Percent complete | How far the task has progressed.
Predecessor | The task that must finish before this one can start.
W1 to W10 | The timeline. A filled cell shows the task is planned for that week.
Tips
• | Colour the week cells to match your own dates if you like.
• | Keep an eye on tasks whose predecessor is running late.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | Leapwise Advisory, delivered with an outside partner.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.