## Cover
Release readiness checklist
Confirm that every step is complete before, during, and after a release.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Release readiness checklist
Confirm that every step is complete before, during, and after a release.
Project | PocketPay (example)
Prepared by | Nirmal Prajapati
Target release date | Add the date
ID | Category | Item | Description | Owner | Status | Showstopper | Evidence or notes | Due date
C1 | Testing and quality | Every step of a payment tested end to end | All paths pass, including failures | QA lead | Ready | Yes | Test results signed off | Add date
C2 | Testing and quality | Security checks confirmed | Access and data checks passed | Security lead | Ready | Yes | Checks passed | Add date
C3 | Data | Any data move checked and reversible | A dry run completed and verified | Data lead | At risk | Yes | Dry run planned | Add date
C4 | Technical | Rollback plan in place if the launch fails | Steps written and tested | Development lead | Ready | Yes | Plan documented | Add date
C5 | Business readiness | A successful payment agreed and understood | Client agrees what good looks like | Project Manager | Ready | No | Agreed with the client | Add date
C6 | Release | Release to a small group first | A small group tries it before everyone | Project Manager | At risk | No | Group being confirmed | Add date
C7 | Support | Support ready to watch closely after launch | A rota is set for the first days | Support lead | Not ready | No | Rota being set | Add date
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Release readiness checklist. How to use this template.
A go or no go checklist for a release, grouped by category, with an owner, a readiness status, and a note on whether an item is a showstopper.
Steps
1 | List each item under its category, for example Testing, Technical, or Support.
2 | Give every item an owner and set the readiness Status.
3 | Mark Showstopper as Yes for items that must be Ready before you can launch.
4 | Hold a go or no go review. If any showstopper is not Ready, the answer is no go.
Columns
Column | What to put in it
Category | The area, for example Testing, Data, Training, Technical, or Support.
Status | Ready, At risk, Not ready, or Not applicable.
Showstopper | Yes if the launch cannot go ahead until this item is Ready.
Evidence or notes | Proof that the item is done, or a note on what is left.
Tips
• | Start the checklist well before the date, so red items have time to be fixed.
• | A single showstopper that is not Ready means no go, however small it seems.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | PocketPay, a payment application released with care.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Release readiness checklist. Summary.
These counts update as you fill in the Template tab.
By readiness
Item | Count
Ready
At risk
Not ready
Not applicable
Showstoppers
Item | Count
Showstopper items
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.