## Cover
Resource and capacity plan
Plan who is needed, with what skills, for how long, and how much of their time.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Resource and capacity plan
Plan who is needed, with what skills, for how long, and how much of their time.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
Role | Name | Skill | Allocation | Start | End | Availability | Notes
Project Manager | Nirmal Prajapati | Delivery | 100% | Week 1 | Week 20 | Full time | Owns the plan
Business analyst | Add name | Requirements | 100% | Week 1 | Week 14 | Full time
Developer | Add name | Build | 100% | Week 4 | Week 15 | Full time | Two developers
QA lead | Add name | Testing | 50% | Week 8 | Week 15 | Part time
Designer | Add name | Design | 50% | Week 2 | Week 10 | Part time
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Resource and capacity plan. How to use this template.
A plan of who is needed on the project, with what skills, for how long, and how much of their time, so the work is properly staffed and nobody is overloaded.
Steps
1 | List each role needed, with the person if known.
2 | Note the skill, and the share of their time the project needs.
3 | Set the start and the end for each one.
4 | Check that nobody is planned at more than their available time.
Columns
Column | What to put in it
Allocation | The share of the person’s time the project needs, for example 100 percent or 50 percent.
Availability | Full time, part time, or as needed.
Tips
• | Add up each person’s allocation across projects. Nobody should be over one hundred percent.
• | Plan the key skills early, before they are needed.
Definitions
Allocation | How much of a person’s working time the project uses.
Availability | Whether the person is full time, part time, or brought in as needed.
Example based on | Make Time Count, a shared case system for several public bodies.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.