## Cover
Risk and issue log
Track risks, assumptions, issues, and dependencies in one place, each with an owner and a response.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Risk and issue log
Track risks, assumptions, issues, and dependencies in one place, each with an owner and a response.
Project | EyezUP (example)
Prepared by | Nirmal Prajapati
Last updated | Add the date
ID | Type | Category | Description | Date raised | Raised by | Owner | Probability | Impact | Severity (1 to 9) | Response or action | Root cause | Status | Target date | Review date
R1 | Risk | Safety | A phone restriction must never block a genuine emergency call | Add date | QA lead | Project Manager | Low | High |  | The emergency exception was built and tested first, in a dedicated round of testing | The rules run before the dialler | Resolved | Add date | Add date
D1 | Dependency | Platform | The rules must behave the same way on Apple and Android | Add date | Mobile lead | Apple and Android leads | Medium | High |  | The behaviour on both devices is reviewed every week | Two different operating systems | In progress | Add date | Add date
A1 | Assumption | Scope | Parents set the limits from the online dashboard | Add date | Business analyst | Product team | Low | Medium |  | Confirmed with the client before the work began | Agreed way of working | Closed | Add date | Add date
I1 | Issue | Quality | Locking behaved differently on some older Android devices | Add date | Tester | Testing team | Medium | Medium |  | Fixed and retested before release | Older device behaviour | Resolved | Add date | Add date
R2 | Risk | Schedule | Store review times could delay the launch | Add date | Project Manager | Project Manager | Medium | Medium |  | Submission planned early, with buffer time held | Outside review queue | Open | Add date | Add date
R3 | Risk | Security | Personal data must be protected in transit and at rest | Add date | Security lead | Security lead | Low | High |  | Encryption and access controls built in from the start | Sensitive personal data | In progress | Add date | Add date
D2 | Dependency | External | The parent dashboard depends on the sign in service | Add date | Backend lead | Backend lead | Low | Medium |  | The sign in service was confirmed and tested early | A shared sign in service | Resolved | Add date | Add date
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Risk and issue log. How to use this template.
A single place to track the risks, assumptions, issues, and dependencies on a project, each with an owner, a severity, and a response.
Steps
1 | Add one row for each item, and give it a short ID (for example R1 for the first risk).
2 | Choose the Type, then set the Probability and the Impact. The Severity is worked out for you.
3 | Give every item an owner and write a clear response or action.
4 | Update the Status as the item moves from Open to Closed. Review the log every week.
Columns
Column | What to put in it
ID | A short reference for the item, so you can point to it in a meeting.
Type | Whether it is a risk, an assumption, an issue, or a dependency.
Category | The area it affects, for example safety, schedule, or quality.
Probability | How likely it is to happen. Used with Impact to work out the severity.
Impact | How much it would affect the project if it happened.
Severity | Probability multiplied by Impact, from 1 to 9. Higher means more urgent.
Response or action | What you are doing about it. For a risk this is the plan to reduce it.
Status | Open, In progress, Resolved, or Closed.
Tips
• | Give every item a single owner. An item with no owner rarely moves.
• | Sort by Severity to see what needs attention first.
• | Close items honestly. A tidy log is one people trust.
Definitions
On track, At risk, Off track | A traffic light view. Green means fine, amber means watch it, red means act now.
Must have, Should have, Could have, Will not have this time | Priority levels. A Must have is essential for this release. A Could have is nice to have. Will not have this time is agreed to leave out for now.
High, Medium, Low | A simple scale used for probability, impact, value, or effort.
Example based on | EyezUP, a road safety application where a genuine emergency must never be blocked.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Risk and issue log. Summary.
These counts update as you fill in the Template tab.
By type
Item | Count
Risks
Assumptions
Issues
Dependencies
By status
Item | Count
Open
In progress
Resolved
Closed
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.