## Cover
Sprint backlog
Hold the work chosen for the current sprint, broken into tasks, with the owner, the estimate, and the status.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Template
Sprint backlog
Hold the work chosen for the current sprint, broken into tasks, with the owner, the estimate, and the status.
Project | Insta Fincorp (example)
Sprint | Sprint 2
Sprint goal | Deliver the loan application
ID | User story or task | Owner | Estimate points | Status | Notes
SB1 | As a customer, I want to apply for a loan, so that I can borrow | Development | 8 | In progress
SB2 | Build the loan review screen | Development | 5 | In progress
SB3 | Match incoming payments to accounts | Development | 6 | To do | Waiting on the payment service
SB4 | Test the loan application end to end | QA lead | 3 | To do
SB5 | Fix the statement totals defect | Development | 2 | Done | Retested
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Sprint backlog. How to use this template.
The work the team has chosen for the current sprint, broken into small tasks, each with an owner, an estimate, and a status, so the team can run the sprint from one place.
Steps
1 | Write the sprint goal at the top.
2 | Pull the chosen stories from the product backlog into this sprint.
3 | Break each story into tasks, and give each an owner and an estimate.
4 | Update the status daily. Finish work before starting more.
Columns
Column | What to put in it
Estimate points | A rough size for the work, used to judge how much fits in a sprint.
Status | To do, In progress, or Done.
Tips
• | Keep the sprint goal in sight. Everything should serve it.
• | Do not add work mid sprint unless something else comes out.
Definitions
Sprint | A short, fixed period in which the team delivers a slice of working product.
Points | A rough measure of size, not hours.
Example based on | Insta Fincorp, a sprint delivering the loan application.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Summary
Sprint backlog. Summary.
These counts update as you fill in the Template tab.
By status
Item | Count
To do
In progress
Done
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.