## Cover
Work breakdown structure
Break the work into core modules and work items, each with a description and an hours estimate, with a subtotal per module and a grand total.
Document control
Project | Add the project
Prepared by | Nirmal Prajapati
Owner | Add the owner
Version | 1.0
Date | Add the date
Status | Draft
Version history
Version | Date | Author | Summary of change
1.0 | Add the date | Nirmal Prajapati | First version
In this workbook
Cover | This sheet. Document control and version history.
Guide | What the template is for, how to use it, what each column means, and the definitions.
Working sheet | The template you fill in. It has example rows you can type over.
Summary | Counts that update as you fill in the working sheet, where included.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## WBS
Work breakdown structure
Break the work into core modules and work items, each with a description and an hours estimate, with a subtotal per module and a grand total.
Project | Make Time Count (example)
Prepared by | Nirmal Prajapati
Version | Add the version
Date | Add the date
Core module | Work item | Description | Estimated hours
Analysis and architecture | Requirements gathering | Agree the scope, needs, and objectives with the bodies | 8
| Information architecture | Agree the structure and the navigation | 4
| Data model design | Design the shared record schema | 6
| Integration design | Agree how the parts connect | 4
Subtotal, Analysis and architecture |  |  | 22
Design | Design system | Reusable components and patterns | 8
| Record screens | Design the shared record and the search | 10
| Reporting screens | Design the manager reports | 6
| Accessibility review | Check the designs meet the standard | 4
Subtotal, Design |  |  | 28
Build, front end | Setup and layout | Project setup, header, and navigation | 6
| Record and search | Build the shared record and the search | 20
| Reporting | Build the reports | 12
| Suggestions | Build the suggestions on a case | 10
Subtotal, Build, front end |  |  | 48
Build, back end | Setup and access | Project setup, sign in, and roles | 8
| Shared record service | Store and update records, and log changes | 24
| Reporting service | Gather and present the figures | 12
| Suggestions service | Generate the suggestions | 12
Subtotal, Build, back end |  |  | 56
Data migration | Extract | Pull the data from the old systems | 6
| Load and check | Load into the new system and verify | 8
Subtotal, Data migration |  |  | 14
Testing and quality | Test plan and cases | Prepare the plan and the cases | 4
| Functional testing | Test across all the parts | 12
| Accessibility testing | Verify the standard | 4
| Security testing | Check access and data | 4
| Bug fixing and retest | Resolve and retest | 8
Subtotal, Testing and quality |  |  | 32
Launch and handover | Deployment setup | Environments and the pipeline | 6
| Go live | Final checks and switch over | 4
| Handover and training | Documents and training | 6
Subtotal, Launch and handover |  |  | 16
Total estimated hours |  |  | 216
Assumptions and notes
• | The estimate assumes a team experienced in the tools used.
• | If the scope changes, the estimate changes with it.
• | The client provides content and access on time.
• | The figures are illustrative and hold no confidential client information.
Notes and commercials
Item | Description |  | Cost
Hosting | Managed hosting for the system |  | To be confirmed
Data sharing agreement | The legal agreement between the bodies |  | To be confirmed
Premium licences | Any premium tools if required |  | Excluded
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.

## Guide
Work breakdown structure. How to use this template.
A breakdown of the whole project into core modules and work items, each with a short description and an estimate in hours. The hours are subtotalled per module and added to a grand total, so it doubles as a detailed estimate.
Steps
1 | List the core modules, the big groups of work, down the left.
2 | Under each module, list the work items, with a short description.
3 | Give each work item an estimate in hours. The subtotals and the total are worked out for you.
4 | Add your assumptions and any commercial items at the bottom.
Columns
Column | What to put in it
Core module | A big group of related work, for example Design or Testing.
Work item | A single piece of work small enough to estimate and own.
Estimated hours | A rough estimate of the effort for the work item.
Subtotal | The hours for a module, added up for you.
Total | The sum of all the subtotals, the whole estimate.
Tips
• | Break work down until each item can be estimated with confidence, then stop.
• | State your assumptions clearly. An estimate without assumptions is easy to misread.
Definitions
Core module | The top level grouping of the work.
Work item | The smallest piece of work you estimate and track.
Estimate | A considered guess at the effort, not a promise. It changes if the scope changes.
Example based on | Make Time Count, broken into modules and estimated in hours.
Template by Nirmal Prajapati. www.heynirmal.com. Illustrative, it holds no confidential client information.